## Sheet1
Name | Sean Dimoff
Date Started: | 25/1/18
Purpose | To look at every sampling method and see how long it would take and how many samples it would get me
Sound Analysis Time
Sampling Scheme: sample x out of y days | 1 every 5 days | 1 every 3 days | Every other day | [5 empty] | Using only the smallest range because all the same dates need to be used to control for tides/weather |  |  |  | Total number of samples under each sampling method
Number of days of recordings | 30 | 45 | 65 |  |  |  | 2017 sampling dates
Number of recordings per day | 4 | 4 | 4 |  | Sites | 32 | 35 | 8 | 5 | 40 | Useable Date Range |  | Year | 1/5 day | 1/3 day | 1/2 day
Total number of recordings (samples) | 120 | 180 | 260 |  | July | 6 to 26 | 6 to 26 | 11 to 26 | 7 to 25 | 6 to 26 | 11 to 25 |  | 2017 | 15 | 25 | 40
Number of recordings removed for divers that day | 12 | 36 | 36 | [9 empty] | 2018 | 10 | 20 | 25
Number of recordings - removed recordings | 108 | 144 | 224 |  |  |  | 2018 sampling dates | [5 empty] | Total samples | 25 | 45 | 65
Weeks to completion if I complete 40/week | 2.7 | 3.6 | 5.6 |  | Sites | 32 | 35 | 8 | 5 | 40 |  |  | Total x 4 per day | 100 | 180 | 260
Date of completion | 2018-02-22 | 2018-03-08 | 2018-03-22 |  | June | 15 to 30 | 16 to 30 | 16 to 30 | 18 to 27 | 15 to 30 | 18 to 27
Sampling Dates: | 1 every 5 days |  |  |  |  | 1 every 3 days |  |  |  |  | 1 every 2 days
| Site |  |  |  |  | Site |  |  |  |  | Site
2017-07-01 | 32 | 35 | 8 | 5 | 40 | 32 | 35 | 8 | 5 | 40 | 32 | 35 | 8 | 5 | 40 | Dates
| 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11
| 16 | 16 | 16 | 16 | 16 | 14 | 14 | 14 | 14 | 14 | 13 | 13 | 13 | 13 | 13
| 21 | 21 | 21 | 21 | 21 | 17 | 17 | 17 | 17 | 17 | 15 | 15 | 15 | 15 | 15
[6 empty] | 20 | 20 | 20 | 20 | 20 | 17 | 17 | 17 | 17 | 17
[6 empty] | 23 | 23 | 23 | 23 | 23 | 19 | 19 | 19 | 19 | 19
[11 empty] | 21 | 21 | 21 | 21 | 21
[11 empty] | 23 | 23 | 23 | 23 | 23
[11 empty] | 25 | 25 | 25 | 25 | 25
2018-06-01 | Site |  |  |  |  | Site |  |  |  |  | Site
| 32 | 35 | 8 | 5 | 40 | 32 | 35 | 8 | 5 | 40 | 32 | 35 | 8 | 5 | 40
| 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | Dates
| 23 | 23 | 23 | 23 | 23 | 21 | 21 | 21 | 21 | 21 | 20 | 20 | 20 | 20 | 20
[6 empty] | 24 | 24 | 24 | 24 | 24 | 22 | 22 | 22 | 22 | 22
[6 empty] | 27 | 27 | 27 | 27 | 27 | 24 | 24 | 24 | 24 | 24
[11 empty] | 26 | 26 | 26 | 26 | 26